## Account Transaction
Table No. 1 Effort Estimation
Sr No. |  | Size of project(FP) | Estimated Productivity | Estimated Efforts(PD)
1 | Login | 56 | 0.7 | 80
2 | Account transactions | 66 | 0.7 | 94
Total |  | 122 | 174
Table No. 2 Cost Estimation
Sr No. | Cost Heads | Efforts(PDs) | Cost/PD | Total Cost
1 | Project cost | 174 | 5819 | 1444200
2 | Overhead cost | 0 | 1745 | 433260
3 | Profit margin | 0 | 872 | 216630
Total |  | 174 | 2094090
Table No. 3
Sr. No. | Distribution of efforts across project |  | % Distribution | Efforts
1 | Requirement analysis |  | 6% | 7.32
2 | Design |  | 10% | 12.2
3 | Coding |  | 32% | 39.04
4 | Unit testing |  | 30% | 36.6
5 | Acceptance testing |  | 12% | 14.64
6 | Management |  | 10% | 12.2
Total |  |  | 100% | 122

## Loan
Table No. 1 Effort Estimation
Sr No. |  | Size of project(FP) | Estimated Productivity | Estimated Efforts(PD)
1 | Login | 56 | 0.7 | 80
2 | Loans | 60 | 0.7 | 85
Total |  | 116 |  | 165
Table No. 2 Cost Estimation
Sr No. | Cost Heads | Efforts(PDs) | Cost/PD | Total Cost
1 | Project cost | 165 | 5819 | 1369500
2 | Overhead cost | 0 | 1745 | 410850
3 | Profit margin | 0 | 872 | 205425
Total |  | 165 |  | 1985775
Table No. 3 Distribution of efforts across project
Sr. No. | Distribution of efforts across project |  | % Distribution | Efforts
1 | Requirement analysis |  | 6% | 7.32
2 | Design |  | 10% | 12.2
3 | Coding |  | 32% | 39.04
4 | Unit testing |  | 30% | 36.6
5 | Acceptance testing |  | 12% | 14.64
6 | Management |  | 10% | 12.2
Total |  |  | 100% | 122